## Sheet1
Activity | Predecessors | days (t)
A | None | 5
B | A | 15
C | A | 5
D | A | 10
E | C and D | 15
F | B and E | 5
G | F | 5
Create a network diagram.
NETWORK DIAGRAM
Slack FORMULA=LS-ES/LF-EF
B
[5 empty] | 15 | 5 | 20
[6 empty] | 15 | 30 |  | F
[6 empty] | Slack = 10 |  |  | 5 | 30 | 35
[10 empty] | 30 | 35
| A | [7 empty] | Slack = 0
| 5 | 0 | 5 | [9 empty] | G
|  | 0 | 5 |  | C | [7 empty] | 5 | 35 | 40
|  | Slack = 0 |  |  | 5 | 5 | 10 | [6 empty] | 35 | 40
Start | [5 empty] | 10 | 15 | [6 empty] | Slack = 0 |  |  | Finish
[6 empty] | Slack = 5 |  |  | E
[9 empty] | 15 | 15 | 30
[10 empty] | 15 | 30
Slack = 0
D
[5 empty] | 10 | 5 | 15
[6 empty] | 5 | 15
Slack = 0
Find out the critical path using critical path method (slack method). | [9 empty] | Critical Path
[9 empty] | Start |  | A | D | E | F | G | Finish
What is the probability that the project will end in:
a. The project will end in 25 days
Standard deviation=1.66
| x=25 |  | z=25-40/1.66 |  |  | Project Compeletion Time=40
z=-9.03
We cannot calculate probability of negative z score of -9.03 so that project will not end in 25 days
Find out the variance for all the critical activities.
|  |  | Activity | Predecessor | Optimistic | Most Likely | Pessimistic | Expected Time | Variance
|  |  | A | - | 4 | 5 | 8 | 5.33 | 0.44
|  |  | B | A | 12 | 15 | 18 | 15
|  |  | C | A | 4 | 5 | 8 | 5.33
|  |  | D | A | 8 | 10 | 12 | 10 | 0.44
|  |  | E | C and D | 12 | 15 | 18 | 15 | 1
|  |  | F | B and E | 4 | 5 | 8 | 5.33 | 0.44
|  |  | G | F | 4 | 5 | 8 | 5.33 | 0.44
|  | Standard deviation=1.66 |  |  |  |  | Varience= |  | 2.76