## Sheet1
Submission by 13275(M. Iftikhar) and 13292(Naeem Ali)
Risk No | Risk Title | Decription of Risk | Owner | Impact | Probablity (%) | Cost Impact (H-M-L) | Scedule Impact (H-M-L) | Mitigation | Probablity after mitigation (%) | Cost of Mitigation
1 | Hosting Down | As the project need 24/7 online stability. So, Down Host result loss in Business | Network Admin and IT Team | High | 60 | H | H | There must be a need of an additional server to minimize the downtime | 5 | Additional Backup Server
2 | Website bugs and Crashes | There can be bugs in sites that are generated due to wrong code. And need to be rectified quickly in order to maintain standards | Developers (front and Back-end both) | High | 80 | H | H | An availability of 24/7 front-end and back-end developers can greatly reduce the upcoming bugs and crashes | < 2 | Paying Extra Salary (overtime)
3 | Employee's role | in the real world scenario, an employee can leave job/ team/ etc. due to any reasson(friends, family,etc.) | Project Manager | Medium | 50 | H | L | Manager should consider hiring a new employee immediately to replace the old one and restore the workflow. | 25 | Searching and Hiring of new Employee
4 | Power/System Failure | Power/ Equipment Failure can be occur anytime which may result in host down, or loss of business, etc. | IT Team | High | 30 | H | H | A secondary hardware is required to overcome the problems of power failures | 0 | Secondary system in case of any failure
5 | Cyber Attack | The Attacks like DDOS, Brutforce or other attacks can result the loss of data and website crash | Network Admin and IT Team | Medium | 60 | L | L | During development phase, the team need to keep it in mind to make sure the website have all the latest seccurity tools to defend the upcoming attack | 10 | Up to date Cyber Security Tools
6 | Estimating/or scheduling errors | Project Manager might miscalculate the completion time for a task and may assign less time to critical tasks or activities | Project Manager | Medium | 30 | L | H | Project Manager should consult with the team members ,when estimating time or scheduling tasks | 5 | none
7 | Lack of Communication | Lack of Communication between all the worker of project may create a huge problematic situation | Project Manager | High | 60 | H | H | It is the Responsibility of Project Manager to manage a good working environment for all the workers and act responsibly in case of any dispute among employees | 25 | none
8 | unavailablity of resource | resources might be unavailable temporarily or might be delayed | Team Leader | High | 50 | H | H | get resources from other providers to maintain workflow. | 25 | new resource cost
9 | Database Crash | Database crash can result whole website down which might problematic for employees to work | DB Adminitrator | Medium | 40 | L | L | It is the Responsibility of Database Administrator to design a database that is capable enough to rectify error rather than generating error or going down | 10 | none
10 | Feasibility for Unplanned Work | Unplanned work can be any demand by client during various phases of development | Project Manager | Medium | 30 | H | H | It is the responsibility of a Project manager to welcome demand by client as well as to manage feasibility to accomplish that task with the planned task | 4 | none