## Table
| TASK | Predecessors | Time (days)
A | Surveys | - | 2 | Submitted by:
B | Interviews | - | 5 |  | M. Iftikhar Uddin Khan Sami | 13275
C | Data Analysis | A,B | 4 |  | Naeem Ali | 13292
D | Use case diagram | C | 3
E | UI Diagram | C | 3
F | ERD | C | 10
G | Schema Design | C | 8
H | DB design | D, E, F, G | 6
I | UI/UX design | H | 15
J | Backend development | I | 20
K | Integration of components | J | 7
L | Testing and usability | K | 10
M | Website design completion | L | 0
N | Debugging | M | 5
O | QA | N | 18
P | Deployment | O | 3
Q | Installation | P | 4
R | Feedback | Q | 2

## Calculation
D
[9 empty] | 3 | 9 | 12
[10 empty] | 34 | 37
Slack = 25
E
|  |  | A | [5 empty] | 3 | 9 | 12
|  |  | 2 | 0 | 2 |  |  |  |  | 34 | 37
|  |  |  | 23 | 25 |  |  |  |  | Slack = 25
|  |  |  | Slack = 23 |  | C | [5 empty] | H
[6 empty] | 4 | 5 | 9 |  |  |  | 6 | 19 | 25 | Slack = 18
[7 empty] | 25 | 29 | F |  |  |  | 37 | 43
|  |  | B |  |  |  | Slack = 20 |  | 10 | 9 | 19
|  |  | 5 | 0 | 5 |  |  |  |  | 27 | 37
|  |  |  | 20 | 25 |  |  |  |  | Slack = 18
Slack = 20
G
[9 empty] | 8 | 9 | 17
[10 empty] | 29 | 37
Slack = 20
M |  |  | L |  |  | K |  |  | J |  |  | I
0 | 77 | 77 | 10 | 67 | 77 | 7 | 60 | 67 | 20 | 40 | 60 | 15 | 25 | 40
| 95 | 95 |  | 85 | 95 |  | 78 | 85 |  | 58 | 78 |  | 43 | 58
| Slack = 0 |  |  | Slack = 18 |  |  | Slack = 18 |  |  | Slack = 18 |  |  | Slack = 18
N |  |  | O |  |  | P |  |  | Q |  |  | R
5 | 77 | 82 | 18 | 100 | 118 | 3 | 118 | 121 | 4 | 121 | 125 | 2 | 125 | 127
| 95 | 100 |  | 100 | 118 |  | 118 | 121 |  | 121 | 125 |  | 125 | 127
| Slack = 18 |  |  | Slack = 18 |  |  | Slack = 0 |  |  | Slack = 0 |  |  | Slack = 0