## Sheet1
| TASK | Predecessors | Time (days)
A | Surveys | - | 2
B | Interviews | A | 3
C | Data Analysis | B | 3
D | Use case diagram | C | 7
E | ERD diagram | C | 12
F | DFD diagram | C | 8
G | WBS | C | 5
H | FDD | C | 5
I | UI/UX design | E | 10
J | database design | I | 12
K | Backend Development | J | 12
L | AR design developing | K | 17
M | Integration of Components | L | 7
N | Testing and Usability | M | 3
O | Debugging/Fixing Bugs | N | 6
P | Software Quality Assurance | O | 13
Q | Deployment Process | P | 5
R | Installation | Q | 5
[12 empty] | D | Slack=5
[13 empty] | 8 | 15
[12 empty] | 7 | 13 | 20
[12 empty] | E | Slack=0
[13 empty] | 8 | 20
[12 empty] | 12 | 8 | 20
|  |  | A | Slack=0 |  | B | Slack=0 |  | C | Slack=0 |  | F | Slack=4 |  | I | Slack=0 |  | J | Slack=0 |  | K | Slack=0 |  | L | Slack=0 |  | M | Slack=0 |  | N | Slack=0 |  | O | Slack=0 |  | P | Slack=0 |  | Q | Slack=0 |  | R | Slack=0
| Start |  |  | 0 | 2 |  | 2 | 5 |  | 5 | 8 |  | 8 | 16 |  | 20 | 30 |  | 30 | 42 |  | 42 | 54 |  | 54 | 71 |  | 71 | 78 |  | 78 | 81 |  | 81 | 87 |  | 87 | 100 |  | 100 | 105 |  | 105 | 110 | Finish
|  |  | 2 | 0 | 2 | 3 | 2 | 5 | 3 | 5 | 8 | 8 | 12 | 20 | 10 | 20 | 30 | 12 | 30 | 42 | 12 | 42 | 54 | 17 | 54 | 71 | 7 | 71 | 78 | 3 | 78 | 81 | 6 | 81 | 87 | 13 | 87 | 100 | 5 | 100 | 105 | 5 | 105 | 110
[12 empty] | G | Slack=7
[13 empty] | 8 | 13
[12 empty] | 5 | 15 | 20
[12 empty] | H | Slack=7
[13 empty] | 8 | 13
[12 empty] | 5 | 15 | 20
Critical Path :A-B-C-E-I-J-K-L-M-N-O-P-Q-R