## Slide 1: Project Management
Critical Path Method (CPM)

## Slide 2
ES – Earliest Start
EF – Earliest Finish
LS – Latest Start
LF – Latest Finish
t – Time
      EF = t + ES
      LS = LF – t

## Slide 3
Activity Name |  | 
t | ES | EF
 | LS | LF

## Slide 4
Forward Movement – Maximum number of days
Backward Movement – Minimum number of days
      Slack: how long an activity can be delayed without extending the finish time.
            Slack = LS – ES / LF – EF
            Slack = 0 -> Critical Activity

## Slide 5: QUESTION:
 | A | B | C | D | E | F | G
P | - | - | A | A,B | D | C,E | E
t | 7 | 9 | 12 | 8 | 9 | 6 | 5

## Slide 6
A
D
B
F
C
G
E

## Slide 7: SOLUTION:
A |  | 
7 | 0 | 7
 | 2 | 9
D |  | 
8 | 9 | 17
 | 9 | 17
C |  | 
12 | 7 | 19
 | 14 | 26
B |  | 
9 | 0 | 9
 | 0 | 9
Slack = 2
Slack = 0
Slack = 7
Slack = 0

## Slide 8
F |  | 
6 | 26 | 32
 | 26 | 32
G |  | 
5 | 26 | 31
 | 27 | 32
E |  | 
9 | 17 | 26
 | 17 | 26
Slack = 0
Slack = 1
Slack = 0

## Slide 10: Important Note
Start listening to the narration from slide 8.
Move in the backward manner that is slide 8 first and 7 after it.
Once you are done with the narration solve the problem in slide 9.
If you still have any issue please feel free to contact me on ridah.fatima@iuk.edu.pk